## Sample
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2018/10/29~2018/11/02 | A. Ongoing Project - 目前執行的Project B. Planning Project - 規劃執行的Project C. Report - 正在執行的Test Report D. Meeting - 預計參加的會議 E. Other - 其他非專案事項 | A. Finished B. Ongoing Project - 實際進行的案件與內容 (進度小節比) i.e. 1. ID_DMS-AAAA EVT Test - Function Test (2/15) - Reliability (1/4) - Performance (1/4) - Po bug 5條 C. Report - 實際進行的Report名稱 (進度百分比) i.e. 1. ID_DMS-BBBB ECO Report_V10_17-Oct-2017 (10%) 2. ID_DMS-CCCC Test Report_V10_17-Oct-2017 (100%) D. Meeting - 實際參加的會議 i.e. 1. KA31 weekly meeting (10/29, 1.5hrs) 2. DMS-XXXX weekly meeting (11/1, 20 min) E. Other i.e. - 清點設備…. | 10/28 PM hold meeting (30min) 10/29 接收xxxx Project (xx/xx~xx/xx) 10/30 請假一天

## 2018_Nov (hidden)
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2018/11/05~2018/11/09 | A. Project 1. POC-W181 SSD ECO - Reliability test: 2. UPOS-510D(PCM-8518) CPU D1 stepping - Function test - Reliability test - Device Finder debug with Arthur 3. PCM-999 USB hub ECO - Function test - Reliability test - Performance test B. Planning Project ignore(new item announced on 11/9, start to record from 11/12) C. Report - UPOS-510D Android/WLAN ECO - POC-W181 SSD ECO - PCM-999 USB hub ECO D. Meeting - 預計參加的會議 E. Other 1. 10G WIFI function with Spirent - UPOS-510D 5G-N WiFi iperf test | A. Finished 1. POC-W181 SSD ECO -Function(1/1) - Reliability(1/1) - Performance(1/1) 2. PCM-999 USB hub ECO -Function(1/1) - Reliability(2/2) - Performance(1/1) 3. UPOS-510D Android/WLAN ECO - Test report B. Ongoing Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (1/5) - Reliability test (0/6) - Performance test (4/4) - Device Finder debug with Arthur 2. UPOS-510D(PCM-8518) Win10 x64 image ECO - Function test (1/4) - Reliability test (0/1) C. Report D. Meeting E. Other 1. 10G WIFI function with Spirent - UPOS-510D 5G-N WiFi iperf test - PWS-870 5G-N Wifi iperf test - Lenovo X210 Wifi iperf test | 11/6 接收PAX-315-STK Project 11/8 Discussed project: PAX-315-STK with PM_Kelvin (30min) 1. Monitor test is the main purpose of this task. 2. Consider the IEC62368 for medical cetification.
2018/11/12~2018/11/16 | A. Project 1. UPOS-510D(PCM-8518) CPU D1 stepping - Device Finder debug with Arthur 2. UPOS-510D(PCM-8518) Win10 x64 image ECO - Function test - Reliability test 3. PAX-315 EVT test - Function test 4. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test B. Planning Project 1. UPOS-510D(PCM-8518) Win10 x86 image ECO 2. UPOS-510F(PCM-8519) ECO with AVL changed C. Report 1. UPOS-510D(PCM-8518) Win10x64 image ECO D. Meeting - (11/16 Fri.) Spirent WiFi AP emulator E. Other - none | A. Finished 1. UPOS-510D(PCM-8518) Win10 x64 image ECO - Function test (4/4) - Reliability test (1/1) B. Ongoing Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (1/5) - Reliability test (2/6) - Performance test (4/4) 2. PAX-315 EVT test - Function test (0/9) - Reliability test (0/2) 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (0/6) - Performance test (0/4) 4. UPOS-510D(PCM-8518) Win10 x86 image ECO - Function test (3/4) - Reliability test (0/1) C. Report 1. UPOS-510D(PCM-8518) Win10 x64 image ECO D. Meeting - (11/16 Fri.) Spirent WiFi AP emulator (~1hr) E. Other 1. 10G WIFI function with Spirent - UPOS-510D 5G-N WiFi iperf test - PWS-870 5G-N Wifi iperf test - Lenovo X210 Wifi iperf test | 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - DeviceFinder issue: Do reboot test for many times, to analyze fail sympton on Transcend HDD with Arthur, finally use the WD HDD instead. - Re-test the S3/S4 test due to the power went off suddenly. 2. PAX-315 EVT test - Some test items like OSD and LED still need to be estimated with PM because the features on the system are diferent with SPEC definition completely. - Re-test the OnOff test due to the power went off suddenly. 11/12 接收 POC-W152C D1 stepping BIOS ECO 11/13 上午請半天 11/17 因停電所以各個案子的長時間測試周末需停止
2018/11/19~2018/11/23 | A. Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test - Reliability test - Performance test 2. PAX-315 EVT test - Function test - Reliability test 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 4. UPOS-510D(PCM-8518) Win10 x86 image ECO - Function test - Reliability test B. Planning Project 1. UPOS-510F(PCM-8519) ECO with AVL changed C. Report 1. UPOS-510D(PCM-8518) Win10x86 image ECO 2. PAX-315 EVT test D. Meeting - none E. Other - none | A. Finished 1. UPOS-510D(PCM-8518) Win10 x86 image ECO - Function test (4/4) - Reliability test (1/1) B. Ongoing Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (5/5) - Reliability test (3/6) - Performance test (4/4) 2. PAX-315 EVT test - Function test (8/9) - Reliability test (2/2) 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (1/6) - Performance test (0/4) C. Report 1. UPOS-510D(PCM-8518) Win10 x86 image ECO D. Meeting - none E. Other - none | 1. PAX-315 EVT test - Contrast Ratio test fail: the customized product doesn't have OSD key so the brightness on monitor can't be adjusted to 100%, keep working with PM/RD to discuus this issue.
2018/11/26~2018/11/30 | A. Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test - Reliability test - Performance test 2. PAX-315 EVT test - Function test - Reliability test 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 4. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test B. Planning Project 1. USC-M3 EVT 2. POC-W152C D1 stepping BIOS ECO test_Standard Product C. Report 1. PAX-315 EVT test D. Meeting - none E. Other - none | A. Finished 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (5/5) - Reliability test (6/6) - Performance test (4/4) B. Ongoing Project 1. PAX-315 EVT test - Function test (9/9) - Reliability test (2/2) 2. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (2/6) - Performance test (0/4) 3. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test (1/1) C. Report 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO D. Meeting - none E. Other - none | 1. PAX-315 EVT test - Contrast Ratio test fail: Confirm the final setting of OSD for shipping, submit one bug to track this issue. 2. POC-W152C D1 stepping BIOS ECO test for Lidco - The result of OnOff test is fail. System keep shutdown status then On off test stop to run. 3. UPOS-510F(PCM-8519) ECO with AVL changed - 2D/3D graphic fail during burn-in test, re-test with Passmark Burn-In V8.1. 11/27 接收 POC-W152C D1 stepping _Standard Product

## 2018_Dec (hidden)
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2018/12/03~2018/12/07 | A. Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 2. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test B. Planning Project 1. USC-M3 EVT 2. POC-W152C D1 stepping BIOS ECO test_Standard Product 3. UPOS-510D Image ECO test C. Report 1. PAX-315 EVT test 2. UPOS-510F(PCM-8519) ECO with AVL changed D. Meeting - none E. Other - none | A. Finished 1. PAX-315 EVT test - Function test (9/9) - Reliability test (2/2) 2. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test (1/1) B. Ongoing Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (2/6) - Performance test (0/4) 2. PAX-315 debug 3. USC-M3 EVT test plan discusstion C. Report 1. PAX-315 EVT test 2. UPOS-510F(PCM-8519) ECO with AVL changed D. Meeting - none E. Other - [12/6] PAX-315 issue debug with 豐藝 (2.5hr) | 1. PAX-315 debug - Contrast Ratio test fail: Co-work with EE to clarify issue, provide the test result for A/D board fine tune. 2. POC-W152C D1 stepping BIOS ECO test for Lidco - EE suggested to use ATX mode for OnOff test. 12/5 接收 UPOS-510D Image ECO test
2018/12/10~2018/12/14 | A. Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 2. PAX-315 debug 3. USC-M3 EVT - Function test - Reliability test B. Planning Project 1. POC-W152C D1 stepping BIOS ECO test_Standard Product 2. UPOS-510D Image ECO test C. Report - none D. Meeting - none E. Other - none | A. Finished 1. PAX-315 debug B. Ongoing Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (5/5) - Reliability test (6/6) - Performance test (4/4) 2. USC-M3 EVT test - Function test (4/15) - Reliability test (0/3) C. Report 1. PAX-315 EVT test 2. POC-W152C D1 stepping BIOS ECO test for Lidco D. Meeting - none E. Other - [12/12] 12G SDI analyzer and generator introduction (1hr) | 1. USC-M3 EVT - OSD test items need to be defined. - USB function can't work so RFID, camera and touch don’t have function - The left side of speak is broken. - LCD show black screen during test. 12/14 請假一天
2018/12/17~2018/12/22 | A. Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 2. USC-M3 EVT - Function test - Reliability test 3. UPOS-510D POSReady7 x32 Image ECO test - Function test - Reliability test B. Planning Project 1. UPOS-510D BIOS ECO test C. Report 1. POC-W152C D1 stepping BIOS ECO test for Lidco D. Meeting - none E. Other - none | A. Finished 1. POC-W152C D1 stepping BIOS ECO test for Lidco B. Ongoing Project 1. USC-M3 EVT test - Function test (12/15) - Reliability test (1/3) 2. UPOS-510D POSReady7 x32 Image ECO test - Function test (4/4) - Reliability test (1/1) 3. POC-W152C D1 stepping BIOS ECO test_Standard Product - Function test (4/5) - Reliability test (1/6) C. Report 1. UPOS-510D POSReady7 x32 Image ECO test D. Meeting - none E. Other - none | 1. USC-M3 EVT - Can't do EVT test: monitor can't be lighted up. 2. POC-W152C D1 stepping BIOS ECO test_Standard Product - Re-test power management test since system BSOD.
2018/12/24~2018/12/28 | A. Project 1. USC-M3 EVT - Function test - Reliability test 2. UPOS-510D POSReady7 x32 Image ECO test - Function test - Reliability test 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test B. Planning Project - none C. Report 1. UPOS-510D POSReady7 x32 Image ECO test D. Meeting - none E. Other - none | A. Finished 1. UPOS-510D POSReady7 x32 Image ECO test 2. USC-M3 EVT test (Test interrupt due to M3 couldn't be power on) B. Ongoing Project 1. POC-W152C D1 stepping BIOS ECO test_Standard Product - Function test (4/5) - Reliability test (2/6) 2. UPOS-510D D1 stepping BIOS for C0 CPU ECO test - Function test (2/5) - Reliability test (2/6) C. Report 1. UPOS-510D POSReady7 x32 Image ECO test D. Meeting - none E. Other - none | 1. POC-W152C D1 stepping BIOS ECO test_Standard Product - System BSOD during reboot test. - System reboot automatically during power management test. - System hang up during On/Off test.

## 2020_January
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2020/12/30~2020/01/03 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Airplane on/off for windows of other resolution. - PassMark for BurnInTest for the quicktest. - Prepare the test automation report for Q1. - ProgrammingIndex by PyQT. - Continuous Intergration Sourcing. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Windows to Go installation for burnintest test methodology. (12/30~12/31) - Windows to Go for USB 3.1 and make sure the auto burnintest should be works. (12/30~12/31) - Verify the airplane mode auto test for UTC 5's DUT and connect the Cisco IP address. (01/02) - Verifyt the airplane mode auto test for Tobbi's DUT and connect the Cisco IP address. (01/03) - Prove the airplane on/off fail rate is a issue of AP or DUT device. (01/02~01/03) | 01/01 Holiday.
2020/01/06~2019/01/10 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Airplane on/off for windows of other resolution. - Prepare the test automation report for Q1. - ProgrammingIndex by PyQT. - Continuous Intergration Sourcing. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the ARP clean code to run auto test for sikuli windows. (01/07~01/08) - Modify the test automation report for Q1 demo document. (01/09) - Coding the programindex code. (01/10) | 01/06 Take a day off.
2020/01/13~2019/01/17 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Airplane on/off for windows of other resolution. - Prepare the test automation report for Q1. - ProgrammingIndex by PyQT. - Continuous Intergration Sourcing. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Merge the code of sikuli and arp. - Add the print stdout and make sure the ouput. - Modify the arp command of airplane on/off code. - Implement the arp clean code for PWS-870. - Implement the arp clean code for Tobbi. - Implement the arp clean code for UTC5. - Modify the Statistic for windows edition. - Study the PyQt5 programing for UI designer. - Implement the program index for FTP connection. - Make the demo report for roaming. - Make the demo report for resolution. - Make the demo report for Luminance. - Make the demo report for PXE. - Implement the program index for MessageBox window.
2020/01/20~2019/01/24 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Airplane on/off for windows of other resolution. - Prepare the test automation report for Q1. - ProgrammingIndex by PyQT. - Continuous Intergration Sourcing. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - morning meeting. (01/21) - | 01/21 morning meeting
2020/01/27~2019/01/31 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - none | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - none