## Sample
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2018/10/29~2018/11/02 | A. Ongoing Project - 目前執行的Project B. Planning Project - 規劃執行的Project C. Report - 正在執行的Test Report D. Meeting - 預計參加的會議 E. Other - 其他非專案事項 | A. Finished B. Ongoing Project - 實際進行的案件與內容 (進度小節比) i.e. 1. ID_DMS-AAAA EVT Test - Function Test (2/15) - Reliability (1/4) - Performance (1/4) - Po bug 5條 C. Report - 實際進行的Report名稱 (進度百分比) i.e. 1. ID_DMS-BBBB ECO Report_V10_17-Oct-2017 (10%) 2. ID_DMS-CCCC Test Report_V10_17-Oct-2017 (100%) D. Meeting - 實際參加的會議 i.e. 1. KA31 weekly meeting (10/29, 1.5hrs) 2. DMS-XXXX weekly meeting (11/1, 20 min) E. Other i.e. - 清點設備…. | 10/28 PM hold meeting (30min) 10/29 接收xxxx Project (xx/xx~xx/xx) 10/30 請假一天

## 2018_Nov (hidden)
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2018/11/05~2018/11/09 | A. Project 1. POC-W181 SSD ECO - Reliability test: 2. UPOS-510D(PCM-8518) CPU D1 stepping - Function test - Reliability test - Device Finder debug with Arthur 3. PCM-999 USB hub ECO - Function test - Reliability test - Performance test B. Planning Project ignore(new item announced on 11/9, start to record from 11/12) C. Report - UPOS-510D Android/WLAN ECO - POC-W181 SSD ECO - PCM-999 USB hub ECO D. Meeting - 預計參加的會議 E. Other 1. 10G WIFI function with Spirent - UPOS-510D 5G-N WiFi iperf test | A. Finished 1. POC-W181 SSD ECO -Function(1/1) - Reliability(1/1) - Performance(1/1) 2. PCM-999 USB hub ECO -Function(1/1) - Reliability(2/2) - Performance(1/1) 3. UPOS-510D Android/WLAN ECO - Test report B. Ongoing Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (1/5) - Reliability test (0/6) - Performance test (4/4) - Device Finder debug with Arthur 2. UPOS-510D(PCM-8518) Win10 x64 image ECO - Function test (1/4) - Reliability test (0/1) C. Report D. Meeting E. Other 1. 10G WIFI function with Spirent - UPOS-510D 5G-N WiFi iperf test - PWS-870 5G-N Wifi iperf test - Lenovo X210 Wifi iperf test | 11/6 接收PAX-315-STK Project 11/8 Discussed project: PAX-315-STK with PM_Kelvin (30min) 1. Monitor test is the main purpose of this task. 2. Consider the IEC62368 for medical cetification.
2018/11/12~2018/11/16 | A. Project 1. UPOS-510D(PCM-8518) CPU D1 stepping - Device Finder debug with Arthur 2. UPOS-510D(PCM-8518) Win10 x64 image ECO - Function test - Reliability test 3. PAX-315 EVT test - Function test 4. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test B. Planning Project 1. UPOS-510D(PCM-8518) Win10 x86 image ECO 2. UPOS-510F(PCM-8519) ECO with AVL changed C. Report 1. UPOS-510D(PCM-8518) Win10x64 image ECO D. Meeting - (11/16 Fri.) Spirent WiFi AP emulator E. Other - none | A. Finished 1. UPOS-510D(PCM-8518) Win10 x64 image ECO - Function test (4/4) - Reliability test (1/1) B. Ongoing Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (1/5) - Reliability test (2/6) - Performance test (4/4) 2. PAX-315 EVT test - Function test (0/9) - Reliability test (0/2) 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (0/6) - Performance test (0/4) 4. UPOS-510D(PCM-8518) Win10 x86 image ECO - Function test (3/4) - Reliability test (0/1) C. Report 1. UPOS-510D(PCM-8518) Win10 x64 image ECO D. Meeting - (11/16 Fri.) Spirent WiFi AP emulator (~1hr) E. Other 1. 10G WIFI function with Spirent - UPOS-510D 5G-N WiFi iperf test - PWS-870 5G-N Wifi iperf test - Lenovo X210 Wifi iperf test | 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - DeviceFinder issue: Do reboot test for many times, to analyze fail sympton on Transcend HDD with Arthur, finally use the WD HDD instead. - Re-test the S3/S4 test due to the power went off suddenly. 2. PAX-315 EVT test - Some test items like OSD and LED still need to be estimated with PM because the features on the system are diferent with SPEC definition completely. - Re-test the OnOff test due to the power went off suddenly. 11/12 接收 POC-W152C D1 stepping BIOS ECO 11/13 上午請半天 11/17 因停電所以各個案子的長時間測試周末需停止
2018/11/19~2018/11/23 | A. Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test - Reliability test - Performance test 2. PAX-315 EVT test - Function test - Reliability test 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 4. UPOS-510D(PCM-8518) Win10 x86 image ECO - Function test - Reliability test B. Planning Project 1. UPOS-510F(PCM-8519) ECO with AVL changed C. Report 1. UPOS-510D(PCM-8518) Win10x86 image ECO 2. PAX-315 EVT test D. Meeting - none E. Other - none | A. Finished 1. UPOS-510D(PCM-8518) Win10 x86 image ECO - Function test (4/4) - Reliability test (1/1) B. Ongoing Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (5/5) - Reliability test (3/6) - Performance test (4/4) 2. PAX-315 EVT test - Function test (8/9) - Reliability test (2/2) 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (1/6) - Performance test (0/4) C. Report 1. UPOS-510D(PCM-8518) Win10 x86 image ECO D. Meeting - none E. Other - none | 1. PAX-315 EVT test - Contrast Ratio test fail: the customized product doesn't have OSD key so the brightness on monitor can't be adjusted to 100%, keep working with PM/RD to discuus this issue.
2018/11/26~2018/11/30 | A. Project 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test - Reliability test - Performance test 2. PAX-315 EVT test - Function test - Reliability test 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 4. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test B. Planning Project 1. USC-M3 EVT 2. POC-W152C D1 stepping BIOS ECO test_Standard Product C. Report 1. PAX-315 EVT test D. Meeting - none E. Other - none | A. Finished 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO - Function test (5/5) - Reliability test (6/6) - Performance test (4/4) B. Ongoing Project 1. PAX-315 EVT test - Function test (9/9) - Reliability test (2/2) 2. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (2/6) - Performance test (0/4) 3. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test (1/1) C. Report 1. UPOS-510D(PCM-8518) CPU D1 stepping ECO D. Meeting - none E. Other - none | 1. PAX-315 EVT test - Contrast Ratio test fail: Confirm the final setting of OSD for shipping, submit one bug to track this issue. 2. POC-W152C D1 stepping BIOS ECO test for Lidco - The result of OnOff test is fail. System keep shutdown status then On off test stop to run. 3. UPOS-510F(PCM-8519) ECO with AVL changed - 2D/3D graphic fail during burn-in test, re-test with Passmark Burn-In V8.1. 11/27 接收 POC-W152C D1 stepping _Standard Product

## 2018_Dec (hidden)
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2018/12/03~2018/12/07 | A. Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 2. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test B. Planning Project 1. USC-M3 EVT 2. POC-W152C D1 stepping BIOS ECO test_Standard Product 3. UPOS-510D Image ECO test C. Report 1. PAX-315 EVT test 2. UPOS-510F(PCM-8519) ECO with AVL changed D. Meeting - none E. Other - none | A. Finished 1. PAX-315 EVT test - Function test (9/9) - Reliability test (2/2) 2. UPOS-510F(PCM-8519) ECO with AVL changed - Reliability test (1/1) B. Ongoing Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (3/5) - Reliability test (2/6) - Performance test (0/4) 2. PAX-315 debug 3. USC-M3 EVT test plan discusstion C. Report 1. PAX-315 EVT test 2. UPOS-510F(PCM-8519) ECO with AVL changed D. Meeting - none E. Other - [12/6] PAX-315 issue debug with 豐藝 (2.5hr) | 1. PAX-315 debug - Contrast Ratio test fail: Co-work with EE to clarify issue, provide the test result for A/D board fine tune. 2. POC-W152C D1 stepping BIOS ECO test for Lidco - EE suggested to use ATX mode for OnOff test. 12/5 接收 UPOS-510D Image ECO test
2018/12/10~2018/12/14 | A. Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 2. PAX-315 debug 3. USC-M3 EVT - Function test - Reliability test B. Planning Project 1. POC-W152C D1 stepping BIOS ECO test_Standard Product 2. UPOS-510D Image ECO test C. Report - none D. Meeting - none E. Other - none | A. Finished 1. PAX-315 debug B. Ongoing Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test (5/5) - Reliability test (6/6) - Performance test (4/4) 2. USC-M3 EVT test - Function test (4/15) - Reliability test (0/3) C. Report 1. PAX-315 EVT test 2. POC-W152C D1 stepping BIOS ECO test for Lidco D. Meeting - none E. Other - [12/12] 12G SDI analyzer and generator introduction (1hr) | 1. USC-M3 EVT - OSD test items need to be defined. - USB function can't work so RFID, camera and touch don’t have function - The left side of speak is broken. - LCD show black screen during test. 12/14 請假一天
2018/12/17~2018/12/22 | A. Project 1. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test 2. USC-M3 EVT - Function test - Reliability test 3. UPOS-510D POSReady7 x32 Image ECO test - Function test - Reliability test B. Planning Project 1. UPOS-510D BIOS ECO test C. Report 1. POC-W152C D1 stepping BIOS ECO test for Lidco D. Meeting - none E. Other - none | A. Finished 1. POC-W152C D1 stepping BIOS ECO test for Lidco B. Ongoing Project 1. USC-M3 EVT test - Function test (12/15) - Reliability test (1/3) 2. UPOS-510D POSReady7 x32 Image ECO test - Function test (4/4) - Reliability test (1/1) 3. POC-W152C D1 stepping BIOS ECO test_Standard Product - Function test (4/5) - Reliability test (1/6) C. Report 1. UPOS-510D POSReady7 x32 Image ECO test D. Meeting - none E. Other - none | 1. USC-M3 EVT - Can't do EVT test: monitor can't be lighted up. 2. POC-W152C D1 stepping BIOS ECO test_Standard Product - Re-test power management test since system BSOD.
2018/12/24~2018/12/28 | A. Project 1. USC-M3 EVT - Function test - Reliability test 2. UPOS-510D POSReady7 x32 Image ECO test - Function test - Reliability test 3. POC-W152C D1 stepping BIOS ECO test for Lidco - Function test - Reliability test - Performance test B. Planning Project - none C. Report 1. UPOS-510D POSReady7 x32 Image ECO test D. Meeting - none E. Other - none | A. Finished 1. UPOS-510D POSReady7 x32 Image ECO test 2. USC-M3 EVT test (Test interrupt due to M3 couldn't be power on) B. Ongoing Project 1. POC-W152C D1 stepping BIOS ECO test_Standard Product - Function test (4/5) - Reliability test (2/6) 2. UPOS-510D D1 stepping BIOS for C0 CPU ECO test - Function test (2/5) - Reliability test (2/6) C. Report 1. UPOS-510D POSReady7 x32 Image ECO test D. Meeting - none E. Other - none | 1. POC-W152C D1 stepping BIOS ECO test_Standard Product - System BSOD during reboot test. - System reboot automatically during power management test. - System hang up during On/Off test.

## 2019_Apr
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/04/01~2019/04/05 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Test Plan review. | A. Finished - none B. Ongoing Project - Test Plan review. C. Report - none D. Meeting - Job description by Raymond. (04/01, 1hr) E. Other - Job trainnig of office environment setting. (04/01, 2hr) - Laptop network environmnet setting by MIS. (04/01, 3hr) - Jean Training (04/01, 2hr) - Job description for weekly report. (04/02, 2hr) - Finished the some courses from e-learning platform. (04/02, 4hr) - Test Plan review. (04/02, 2hr) - Test Plan review (04/03, 8hr)
2019/04/08~2019/04/12 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Test Plan review - Implement the roaming situation. | A. Finished - none B. Ongoing Project - Test Plan review. C. Report - none D. Meeting - Weekly Meeting. (04/11, 4hr) E. Other - Test Plan review (04/08, 8hr) - Make sure the roaming situation is worked or not. (04/09, 8hr) - Implemention the roaming mode. (04/10, 8hr) - Implemention the roaming mode. (04/11, 4hr) - System structure training of Jada. (04/12, 4hr) - Make sure the roaming should be worked with Aimesh. (04/12, 4hr)
2019/04/15~2019/04/19 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Test Plan review. - Deal with the python 3x of environment questions. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - Discuss the test process milestone with Raymond. (04/15, 1hr) E. Other - PWS-870 Spec review. (04/15, 4hr) - UTK-520F&532F Spec review. (04/15, 3hr) - Setting the software environment for python 3x. (04/16, 4hr) - Jean Training for CPU, USB of function test. (04/16, 2hr) - Deal with the python 3x of environment questions. (04/16, 2hr) - Jean Training for Display of function test. (04/17, 2hr) - Deal with the vc++ complier problem for python 3.6.8. (04/17, 3hr) - Make sure the wifi AP of roaming situation. (04/17, 3hr) - Implement the wifi router base on different ip address. (04/18, 8hr) - Jean Training for NFC, MSR, Barcode of function test. (04/19, 2hr) - Deal with the python 3x of environment questions. (04/19, 6hr)
2019/04/22~2019/04/26 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - Employee training (05/02) E. Other - Test Plan review. - Implement the roaming code of test cases. (~05/09) - Implement the login function of test case code. (~04/26) - Try to solve the "assertConfirmation" problem. (~04/30) - Try to solve the frame problem. (~04/26) | A. Finished - none B. Ongoing Project - Test Plan review. C. Report - none D. Meeting - Weekly Meeting. (04/25, 4hr) E. Other - Implement the wifi roaming test case for automation. (04/22, 6hr) - Jean training for WLAN and WWAN of function test. (04/22, 2hr) - Leave Request. (04/23) - Jean training for Touch Panel, Bluetooth and RFID of function test. (04/24, 2hr) - Implement the open_the_browser function of test cases code. (04/24, 3hr) - Implement the mac_address_check function of test cases code. (04/24, 3hr) - Implement to solve the restart function of test cases code. (04/25, 2hr) - Implement to deal with the assertConfirmation problem. (04/25, 2hr) - Implement to solve the frame problem. (04/26, 8hr) | Leave Request (04/23)

## 2019_May
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/04/29~2019/05/03 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Test Plan review. - Finished the ping function of test case code. - Finished the roaming code. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Jean training for CPU, memory and storage device of function test. (04/29, 2hr) - Implement to solve the pytoexe error. (~04/30) - Implement the logger library export. (04/29, 4hr) - Implement the sys.argv[] fuction. (04/29, 2hr) - Implement the A to B switch time. (04/29, 2hr) - Implement the pytoexe error. (04/30, 4hr) - Implement the threading fuction and method when reboot the repeater. (04/30, 4hr) - Implement the interval time problem. (05/03, 4hr) - Implement the "num34" installer base on "pip installer pyinstaller" error. (05/03, 4hr) - Finish the roaming SOP document. (05/04, 4hr) - Run the code base on 100 cycles. (05/04, 4hr)
2019/05/06~2019/05/10 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Try to finish the internal time problem. - Make sure the test cases of long term roaming. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Merge the roaming code. (05/06, 4hr) - Implement the 100 cycle ones again. (05/06, 4hr) - Write the SOP of roaming test cases. (05/07, 8hr) - Slove the internal time problem, maybe try to use the ip address 'arp -a IP' mothod. (05/08, 8hr) - Implement the 'arp -a' internal time function and method. (05/09, 8hr) - Slove the administrator command line problem. (05/10, 4hr) - Implemen the arp clear batch base on administrator. (05/10, 2hr) - Join the arp -d command line base on power shell. (05/10, 2hr)
2019/05/13~2019/05/17 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Coding the backup data method. - Test Plan Review. | A. Finished - none B. Ongoing Project - (2711-013) AMIS-50E USB ECO Test (05/22) - Function Test (1/1) - Reliability Test (0/2) - Performance Test (1/1) C. Report - none D. Meeting - none E. Other - Implement the backup data method. (05/13, 8hr) - Test Plan Review. (05/14, 4hr) - Research the flask and swagger API used. (05/14, 4hr) - Set up the test automation environment for other DUT. (05/15, 4hr) - Finished the sop for wifi roaming code. (05/15, 4hr) - Warm boot test. (05/16 over night) - Software installer for Chrome browser installation of SOP. (05/16, 4hr) - Software installer for Python 3.6.8 installation of SOP. (05/16, 4hr) - Burn In Test. (05/17 over night) - Software installer for Wi-Fi roaming of automated testing of SOP. (05/17, 8hr)
2019/05/20~2019/05/24 | A. Ongoing Project - (2711-013) AMIS-50E ECO Test (05/22) B. Planning Project - none C. Report - none D. Meeting - none E. Other - Research the appium server base on pad computer of test procedure. - Research the cisco wifi roaming. | A. Finished - (2711-013) AMIS-50E USB ECO Test (05/22) - Function Test (1/1) - Reliability Test (2/2) - Performance Test (1/1) B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Finish the roaming SOP document. (05/20) - Finish the AMIS-50E USB ECO Test Report. (05/21) - Research the cisco wifi by handover. (05/22) - Implement the airplane mode shell be work on Pad. (05/22) - Try to solve the windows alert problem when login. (05/23) - Planing the test procedure by handover. (05/23) - Implement the wifi shall be work when aireplane is ON/OFF by adb command. (05/24)
2019/05/27~2019/05/31 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the airplane mode shell be work on Pad. - Research the cisco handover. - To Plan the test procedure by handover. - To solve the windows alert problem. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Implement the wifi shall be work when aireplane is ON/OFF by adb command. (05/27~05/29) - Try to use the adb command to control the airplane mode on and off. (05/27) - Discuss the airplane mode if it's have any problem base on the day of 27 to 29. (05/27~05/29) - Implement the wifi handover by cisco Access Point base when the AP doesn't reboot. (05/30~05/31)

## 2019_June
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/06/03~2019/06/07 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Coding the cisco roaming. (Pending) | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Run airplane program by five thousand times. - Implement the wifi handover by cisco Access Point base when the AP doesn't reboot. (06/03) - Behavior the db switch problem. (06/04) - Behavior ping outside problem. (06/05) - To plan the cisco roaming test procedure. (06/03~06/06) - Solve the roaming -128~128 cannot switch. (06/05)
2019/06/10~2019/06/14 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Coding the airplane WAN and LAN code. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the cisco roaming. (06/10~06/14) (Pending) - Modify the sop document. (06/10) - Coding the airplane_wwan. (06/10~06/14) - Coding the airplane_wwan_single. (06/10~06/11) - Coding the airplane_wwan_multi. (06/12~06/14) - Make sure the code should be work on multi device. (06/13)
2019/06/17~2019/06/21 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Coding the airplane WAN and LAN code. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Leave request. (06/17) - Make sure the ethernet can worked on ADB command line. (06/18) - Verify the WHCK Secure Boot test. (06/18) - Coding the airplane_ethernet_single for wlan. (06/18~06/19) - Coding the airplane_ethernet_single for wwan. (06/18~06/19) - Behavior the RJ-45 adb connect problem. (06/18) - Coding the aireplane_ethernet_multiple for wlan. (06/20、06/24) - Coding the aireplane_ethernet_multiple for wwan. (06/20、06/24) | Leave request. (06/17) Intel Solution Day (06/21)
2019/06/24~2019/06/28 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Maintain the aireplane_ethernet_multiple code. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the "rm -rf /mnt/sdcard/airplane_*.jpg" code. (06/24) - Modify the judgment the "packet loss" function. (06/24) - Finished the SOP of ethernet by WLAN and WWAN. (06/25) - Coding the aireplane_ethernet_multiple for wlan. (06/26~06/28) - Coding the aireplane_ethernet_multiple for wwan. (06/26~06/28)

## 2019_July
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/07/01~2019/07/05 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Research the opencv API solution. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Prepare the "test automation" report. (07/01~07/02) - Resolve the PY to EXE problem. (07/02) - Research the opencv API solution. (07/03~07/05) - Implement the image processing method. (07/03~07/05)
2019/07/08~2019/07/12 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the image processing | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the screenshot lib. (07/09) - Implement the cv.py of reboot function. (07/09) - Coding the compare_image lib. (07/10) - Coding the diff lib. (07/11) - Implement the cv.py of add the failed image title. (07/10~07/11) - Finished the aireplane_ethernet_multiple for wlan SOP. (07/12) - Finished the aireplane_ethernet_multiple for wwan SOP. (07/12) | Leave a day. (07/08)
2019/07/15~2019/07/19 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the image processing | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the cv_original lib. (07/15) - Implement the cv_compare .py. (07/16) - Implement the cv_original .py. (07/16) - Resolved the auto run the cv_compare.py code when the DUT is reboot. (07/17) - Try to implement the ignore the numbers when the cv_compare is running. (07/18~07/19)
2019/07/22~2019/07/26 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the image processing - Implement the resolution - Computer Reinstall | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Set the Programming Environment. (07/22~07/23) - Implement the resolution code. (07/24~07/25) - Implement the image processing. (07/26)

## 2019_August
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/07/29~2019/08/02 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the resolution code - Reinstall the computer requirement. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Implement the resolution code. (7/30~7/31) - Reinstall the computer requirement. (7/30) - Study the panel spec. (7/30~7/31) - Research the panel demand, study the panel document. (8/1~8/2) - AP protocol research. (n, ac, lagecy) (8/1) - Research the windows Wi-Fi on/off solution. (8/2) - Coding the panel demand. (8/2) | 7/29 Leave a day off.
2019/08/05~2019/08/09 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Research "Panel" demand. - Modify the resolution code. - Research AP protocol method. (a, b, g, n, ac) - Graphic demand. (drawing shape code) - Touch Panel demand. (luminace pattern) - PXE auto installer. - Research Program_Index application. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the luminace_pattern code. (08/05~08/08) - Coding the drawing shape code. (08/05~08/06) - Make sure the resolution code can be executed. (08/05)
2019/08/12~2019/08/16 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Research "Panel" demand. - Research AP protocol method. (a, b, g, n, ac) - Touch Panel demand. (luminace pattern) - PXE auto installer. - Research Program_Index application. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the luminace code base on panda moniter. (08/12~08/14) - Coding the luminace code for initial function. (08/15) - Coding the luminace code for calculator. (08/16) - Coding the luminace code for calculator edge. (08/16)
2019/08/19~2019/08/23 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Research AP protocol method. (a, b, g, n, ac) - Coding the windows airplane mode on/off. - Research the PXE auto installer. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Write the SOP of luminance patter code. (08/16) - Write the SOP of resolution code. (08/19) - Write the SOP of drawing_shape code. (08/19) - Coding the windows airplane mode on/off. (08/19~08/21) - Write the SOP of window command airplane mode on/off code. (08/21) - Coding the AP protocol method. (08/21~08/23) - Make sure the problem of AP to outside connection fail or DUT to security gateway of AP fail. (08/21) - Coding the AP to security gateway code. (08/21)
2019/08/26~2019/08/30 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the AP protocol method. (a, b, g, n, ac) | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Write the SOP of windows command airplane mode on/off. (08/26~08/27) - Implement the AP protocol method. (08/28~08/30) - Implement the run_script method. (08/28) - Implement the reconnect wifi issue for the AP. (08/29) - Implement the switch_mode method. (08/30)

## 2019_September
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/09/02~2019/09/06 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the AP switch protocol method. (a, b, g, n, ac) | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Join the Wireless_switch.py by the ap switched. (09/02) - Write the SOP of wireless_switch code. (09/03) - Verify the issue by the AP switch error problem. (09/04~09/06) - Implement the run_script method. (09/04) - Implement the reconnect_wifi method. (09/05)
2019/09/09~2019/09/13 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the AP switch protocol method. (a, b, g, n, ac) - Research the ProgramIndex application. - Research the PXE installer. - Research the catch the id and mechanical arm. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Implement the wireless_switch code. (09/09) - Verify the issue by the AP switch error problem. (09/09~09/10) - Verify the run_script method. (09/09) - Verify the reconnect_wifi method. (09/09) - Finished the SOP of wireless switch. (09/10) - Study the ProgramIndex application SOP. (09/11) - Research the catch the id with windows form. (09/12)
2019/09/16~2019/09/20 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the AP switch protocol method. (a, b, g, n, ac) - Research the ProgramIndex application. - Research the PXE installer. - Research the catch the id and mechanical arm. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Make sure the Roaming by the Jean's case. (09/16) - Retest the AP switch mode code by other DUT. (09/17) - Teach Yvonne of the lumance test procedure. (09/18) - Retest the AP switch mode code by other DUT. (09/19) - Maintain the ProgramIndex application. (09/20)
2019/09/23~2019/09/27 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Implement the AP switch protocol method. (a, b, g, n, ac) - Research the PXE installer. - Research the ProgramIndex application. - Research the catch the id and mechanical arm. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Modify the wireless switch code by 5G of asus router's UI. (09/23) - Make sure the 5G mode of load test performance. (09/23) - Implement the ProgramIndex application SOP. (09/23) - Make sure the 2.4G mode of load test performance. (09/24) - Research the catch the id with windows form. (09/24) - Retest the Roaming and write the SOP by case. (09/25) - Try to catch the windows form location by autoit tool. (09/26) - Reserach the PXE installer by unattended win10 using WDS on win server 2012 R2. (09/27)

## 2019_October
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/09/30~2019/10/05 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Change the code and sop location and git commit and push command. (10/01) - Modify and retest the ping security gateway for all program. (10/02) (Ethernet of Wireless LAN and WAN automated testing, Wireless LAN and WAN automated testing, Airplane mode by windows command of Wireless LAN and WAN automated testing, Roaming of automated testing, wireless_switch/Wireless auto switch base on AP repeater) - Modify all of the sop document. (10/03) (Ethernet of Wireless LAN and WAN automated testing, Wireless LAN and WAN automated testing, Airplane mode by windows command of Wireless LAN and WAN automated testing, Roaming of automated testing, wireless_switch/Wireless auto switch base on AP repeater) - Run the roaming by 10 cycles and set the security gateway for 192.168.50.1 ip address. (10/04) - Research the PXE installer for the XML date. (10/05) | 09/30 颱風假 10/05 補班
2019/10/07~2019/10/11 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Graphic the system stracture. (10/07) - Implement the PXE installer for the XML data. (10/07) - Make sure the WSIM of xml environment setting. (10/08) - Discuss with Jada by the MDT application installation with xml file of relationship. (10/08) - Implement the xml auto installation procedure. (10/09) | 10/10~10/11 連假
2019/10/14~2019/10/18 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Arrange the summary table for all program process. (10/14) - Implement the UEFI of auto test by PXE installer. (10/14~10/15) - Resolved the product key resolution. (10/15) - Implement the Legacy of auto test by PXE installer. (10/16~10/17) - Resolved the parameter of WSIM clg problem. (10/16) - Implement the UEFI of x64 and Legacy of x64, x86 problem. (10/16) - Implement the Legacy of 32 bit by win10 auto installation. (10/17) - Implement the Legacy of 64 bit by win10 auto installation. (10/17) - Create the pxe of sop and standard operation procedure of UEFI and Legacy. (10/18) - Write the sop of the pxe auto installation by the UEFI and Legacy procedure. (10/18)
2019/10/21~2019/10/25 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Android 8.1 for WLAN ans WWAN of airplane mode - Auto Installation by PXE Server static ip address. - Tensorflow Operation of GPU speed up. - ProgrammingIndex by PyQT. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Implement the sop of the PXE's UEFI execution testing process. (10/21) - Implement the sop of the PXE's UEFI by IPV4 execution testing process. (10/21) - Implement the sop of the PXE's UEFI by IPV6 execution testing process. (10/22) - Implement the sop of the PXE's Legacy base on x86 execution testing process. (10/22) - Implement the sop of the PXE's Legacy base on x64 execution testing process. (10/22) - Implement the sop of the PXE's environment setting by auto testing parameter of xml files. (10/23) - Merge the pxe folder and xml file to git server and mantain the test process. (10/23) - Implement the wlan of ethernet and wlan of single airplane base on Android 8.1. (10/24) - Implement the wlan of ethernet and wlan of single airplane base on Android 8.1. (10/25)
2019/10/28~2019/11/01 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Android 8.1 for WLAN ans WWAN of airplane mode - Auto Installation by PXE Server static ip address. - Tensorflow Operation of GPU speed up. - ProgrammingIndex by PyQT. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Implement the wlan of ethernet and wwan of multi airplane base on Android 8.1. (10/28) - Implement the wlan of ethernet and wwan of multi airplane base on Android 8.1. (10/29) - Research the Tensorflow Operation of GPU speed up. (10/30~11/01) - Anaconda the visual space by the tensorflw-gpu and python 3.5.0 edition. (10/30) - Resolved the NVIDIA graphics driver installation error. (10/31) - Installation the CUDA 8.0 problem. (11/01) - Discusstion the CUDA 8.0 and Geforce GTX 1600 display card error. (11/01) - Discusstion the ROCm for AMD GPU performance. (10/31~11/01)

## 2019_November
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/11/04~2019/11/08 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - Tensorflow by MXX of GPU speed up. (Pending) - ProgrammingIndex by PyQT. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - To execute the USM-210 windows airplane mode for auto test. (11/05) - Understand the MXX of GPU base on "SG" external display card by BIOS setting. (11/05) - Clarify the problem of USM-210, because the LTE module is crashed. (Pass/Fail: 603/397) (11/06) - Clarify the Widows only disable airplane mode problem. (11/06) - Implemnet the three partition operation system of windows 2012 center R2. (11/06~11/07) - Research the Color Sensor by arduino for auto reboot setting. (11/06~11/07) - Discuss the windows domain setting. (11/07) - Make sure the ProgrammIndex program excution and build the FTP server to recheck the tools could be works or not. (11/07) - To understand the windows domain, DHCP, WDS and FTP environment setting. (11/08) | 11/04 Take day off.
2019/11/11~2019/11/15 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - Tensorflow by MXX of GPU speed up. (Pending) - ProgrammingIndex by PyQT. - PassMark for BurnInTest reliability. - Mechanical arm AutoIT method. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Setting and installing the Windows domain, DHCP, WDS, FTP environment for UEFI of x64. (11/11) - Setting and installing the Windows domain, DHCP, WDS, FTP environment for Legacy of x64. (11/12) - Setting and installing the Windows domain, DHCP, WDS, FTP environment for Legary of x86. (11/12) - ProgramIndex tool of research. (11/12~11/13) - Implement the arduino intergration with PXE auto installation methodology. (11/12) - Prepare the personal report. (11/12~11/13) - Writing the SOP of pxe full auto test automation. (11/13) - Research the PassMark for BurnInTest tool reliability. (11/14~11/15) - Research the ProgramIndex "No find" file or folder problem. (11/14~11/15)
2019/11/18~2019/11/22 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - PassMark for BurnInTest reliability. - Mechanical arm AutoIT method. - CI Sourcing. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Implement the catch code of WDS log from PXE Server. (11/18~11/20) - Coding the application evtx to txt code. (11/19) - Coding the operation evtx to txt code. (11/20) - Make sure the WDS installation start time and end time for one cycle. (11/19) - ProgramIndex Research. (11/20~11/22) - Design the ProgramIndex icon and function location. (11/21~11/22) - BurnInTest Research. (11/18~11/19) - Try to run the BurnInTest of load testing and search the log result. (11/21) - Design the UI control base on BurnInTest feasibility and log result display. (11/22)
2019/11/25~2019/11/29 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - PassMark for BurnInTest for the quicktest. - Mechanical arm AutoIT method. - CI Sourcing. - Prepare the test automation report for Q1. - Airplane on/off for windows of other resolution. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the timer read and writing base on application and operation log. (11/25~11/26) - Finished the WDS other DUT system environment setting. (11/26) - Setting the ubuntu OS base on window system. (11/27~11/28) - Implement the three pxe server build. (11/27) - Airplane for windows resolution. (11/28) - Continuou intergration base on Ubuntu 18.04 environment setting. (11/28) - Set the ubuntu 18.04 environment base on windows x64 os. (11/29) - Study the BurnInTest USB AutoRun documnet. (11/29) - ProgramIndex Design by PyQT User interface. (11/29)

## 2019_December
Date | 工作事項 |  | Note
| 周一 (10:00前) | 周五 (17:30前)
2019/12/02~2019/12/06 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - PassMark for BurnInTest for the quicktest. - Mechanical arm AutoIT method. - CI Sourcing. - Prepare the test automation report for Q1. - Airplane on/off for windows of other resolution. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Take a day off. (12/02) - Verify the GSM-210 auto test base on Android 8.1 for ethernet RJ-45 test. (12/03) - Support Willie for the GSM-210 manual test by the COM port problem. (12/03) - Run the resolution code on the GSM-210 resolution test. (12/03) - Make sure the PXE code on the operation txt and application txt data. (12/04) - Try to resolve the pxe code for "error" read and write error. (12/04) - Make sure the PXE Server log export date. (12/04) - Study the Postman & Jenkins & Github application for chapter 1, 2 for postman. (12/05) - Prepare the test automation report for Q1. (12/06) | 12/02 Take day off.
2019/12/09~2019/12/13 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - Auto Installation by PXE Server static ip address. - ProgrammingIndex by PyQT. - PassMark for BurnInTest for the quicktest. - Mechanical arm AutoIT method. - CI Sourcing. - Prepare the test automation report for Q1. - Airplane on/off for windows of other resolution. | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - Coding the ProgramIndex by PyQT form. (12/09~12/13) - Build the CI Sourcing resoure. (12/10~12/12) - BurnInTest USB Flash Driver running research. (12/09~12/11)
2019/12/16~2019/12/20 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - none | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - none
2019/12/23~2019/12/27 | A. Ongoing Project - none B. Planning Project - none C. Report - none D. Meeting - none E. Other - none | A. Finished - none B. Ongoing Project - none C. Report - none D. Meeting - none E. Other - none